FORM AM 1262								                                                        		           APPROVED    R. Abernethy (signed)                              DATE     9/16/58

SCHEDULE NO. ______20       ___      DATE   9-12-58                                                 MONTHLY BUILDING SCHEDULE                                                         APPROVED      R. W.Chapin Jr.  (signed)                        DATE_    9/16/58               _

REVISION NO. _______     ______      DATE                                                                                  PRODUCT                                                                                         APPROVED       E.W.Bernitt       (signed)                        DATE _   9-16-58             ____

FINAL	SERIES III 1500 c.c. ENGINE

METROPOLITAN SERIES CARS – AUSTIN MOTORS CO., LTD, ENGLAND

| DESCRIPTION | BUILT (ACT( EST THRU AUGUST | FIRM BUILDING SCHEDULE (FABRICATED MATERIAL RELEASE) | TENTATIVE SCHEDULE (RAW MATERIAL RELEASED) | GRAND TOTAL |
| --- | --- | --- | --- | --- |
|  |  | MONTH SEPTEMBER DAYS 22 | MONTH OCTOBER DAYS 23 | MONTH NOVEMBER DAYS 20 | MONTH DECEMBER DAYS 21 | MONTH JANUARY 1959 DAYS 7 | MONTH DAYS |  |
|  |  | DAILY | MONTH | CUM’L TOTAL | DAILY | MONTH | CUM’L TOTAL | DAILY | MONTH | CUM’L TOTAL | DAILY | MONTH | CUM’L TOTAL | DAILY | MONTH | CUM’L TOTAL | DAILY | MONTH | CUM’L TOTAL |  |
| DOMESTIC LHD: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hard-Top | 24653 |  | 1065 | 25718 |  | 1116 | 26834 |  | 937 | 27771 |  | 718 | 28489 |  | 241 | 28730 |  |  |  |  |
| Soft-Top | 4151 |  | 78 | 4229 |  | 122 | 4351 |  | 111 | 4462 |  | 81 | 4543 |  | 39 | 4582 |  |  |  |  |
| Total U.S. | 28804 | 60.0 | 1143 | 29947 | 53.8 | 1238 | 31185 | 52.4 | 1048 | 32233 | 38.0 | 799 | 33032 | 40.1 | 280 | 33312 |  |  |  |  |
| Over/(Under) Schedule 19 | 41 |  | 39 | 80 |  | 67 | 147 |  | 398 | 545 |  | 42 | 587 |  | 32 | 619 |  |  |  |  |
| FOREIGN: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EXPORT LHD Hard-Top | 789 |  | 27 | 816 |  | 20 | 836 |  | 20 | 856 |  | 20 | 876 |  | -0- | 876 |  |  |  |  |
| Soft-Top | 367 |  | 19 | 386 |  | 10 | 396 |  | 10 | 406 |  | 10 | 416 |  | -0- | 416 |  |  |  |  |
| Total Export LHD | 1156 |  | 46 | 1202 |  | 30 | 1232 |  | 30 | 1262 |  | 30 | 1292 |  | -0- | 1292 |  |  |  |  |
| RHD Hard Top | 355 |  | 11 | 366 |  | 10 | 376 |  | 10 | 386 |  | 10 | 396 |  | -0- | 396 |  |  |  |  |
| Soft Top | 60 |  | 6 | 66 |  | 3 | 69 |  | 3 | 72 |  | 3 | 75 |  | -0- | 75 |  |  |  |  |
| Total Export RHD | 415 |  | 17 | 432 |  | 13 | 445 |  | 13 | 458 |  | 13 | 471 |  | -0- | 471 |  |  |  |  |
| Total Export LHD & RHD | 1571 | 2.9 | 63 | 1634 | 1.9 | 43 | 1677 | 2.1 | 43 | 1720 | 2.1 | 43 | 1763 | 0.0 | -0- | 1763 |  |  |  |  |
| Over/(Under) Schedule 19 | (70) |  | (12) | (82) |  | (22) | (104) |  | (32) | (136) |  | (22) | (158) |  | (24) | (182) |  |  |  |  |
| CANADA Hard-Top | 2435 |  | 75 | 2510 |  | 25 | 2535 |  | 45 | 2580 |  | -0- | 2580 |  | -0- | 2580 |  |  |  |  |
| Soft-Top | 242 |  | -0- | 242 |  | -0- | 242 |  | -0- | 242 |  | -0- | 242 |  | -0- | 242 |  |  |  |  |
| Total Canada | 2677 | 3.4 | 75 | 2752 | 1.1 | 25 | 2777 | 2.3 | 45 | 2822 | 0 | -0- | 2822 | 0.0 | -0- | 2822 |  |  |  |  |
| Over/(Under) Schedule 19 | (3) |  | 5 | 2 |  | (45) | (43) |  | (32) | (75) |  | (20) | (95) |  | (8) | (103) |  |  |  |  |
| Total Foreign | 4248 | 6.3 | 138 | 4386 | 3.0 | 68 | 4454 | 4.4 | 88 | 4542 | 2.1 | 43 | 4585 | 0.0 | -0- | 4585 |  |  |  |  |
| Over/(Under) Schedule 19 | (73) |  | (7) | (80) |  | (67) | (147) |  | (64) | (211) |  | (42) | (253) |  | (32) | (285) |  |  |  |  |
| GRAND TOTALS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hard-Top | 28232 | 53.5 | 1178 | 29410 | 50.9 | 1171 | 30581 | 50.6 | 1012 | 31593 | 35.6 | 748 | 32341 | 34.5 | 241 | 32582 |  |  |  |  |
| Soft-Top | 4820 | 4.7 | 103 | 4923 | 5.9 | 135 | 5058 | 6.2 | 124 | 5182 | 4.5 | 94 | 5276 | 5.6 | 39 | 5315 |  |  |  |  |
| Total | 33052 | 58.2 | 1281 | 34333 | 56.8 | 1306 | 35639 | 56.8 | 1136 | 36775 | 40.1 | 842 | 37617 | 40.1 | 280 | 37897 |  |  |  |  |
| Over/(Under) Schedule 19 | (32) |  | 32 | -0- |  | -0- | -0- |  | 334 | 334 |  | -0- | 334 |  | -0- | 334 |  |  |  |  |